## Sheet1
start date | task
2019-11-27 | Assessment 1: Project Scoping and Planning
WP1
2019-11-27 | Research the different types of bike components
2019-12-02 | Create a set of weighted criteria for choosing the base technology for the frame kit
2019-12-07 | Look for available technologies online
2020-01-26 | Look for available technologies in brick and mortar shops
2020-01-29 | Score each technology based on the weighted criteria chosen earlier
2020-01-30 | Choose products that work well together from the top scoring options
WP2
2020-02-03 | Create simplified CAD models of recommended components
2020-02-03 | Develop and refine concepts for one or two initial geometries
2020-02-06 | Put together a kit with preliminary angles, lengths, and quantities of components based on concepts
2020-02-07 | Create initial and alternative geometries from the kit and assess if they are fit for purpose
2020-02-10 | Adjust lengths, angles, and quantities of components in the kit
2020-02-12 | Repeat until geometries are optimised
2020-02-19 | Analyse final geometries eg. Force calculations
2020-02-26 | Decide which components should be in the starter kit and which should be add-ons
WP3
2020-02-15 | Source materials eg tubes
2020-02-27 | Cut profiles to length etc.
2020-02-27 | Fabricate any custom parts needed
2020-02-15 | Source bicycle components eg gears
2020-03-03 | Assessment 2: Preliminary Project Presentations
2020-03-05 | Assemble the bicycle
2019-03-12 | Conduct testing, ie strain gauges, feedback from target market
WP4
2019-11-27 | Set up GitHub repository
Learn MarkDown syntax
Track progress throughout project
Write instructions on the use of the kit, based on best practice
Compile and finalise documantation
Report
2020-03-28 | Compile design logs, test reports, etc.
Reflect on how the project could be developed in the future
Plan structure of report
List and gather all figures needed
Create report skeleton
Draft each section
Revise drafts
Work on formatting and graphics
Create bibliography from references (which should be collected throughout)
2020-04-29 | Assessment 3: Final Project Report
2020-05-11 | Assessment 5: Viva, Final Presentation and Poster
2020-05-25 | Exhibition, External Viva