## Sheet1
from prelim: | start date | task
2019-11-27 | 2019-11-27 | Assessment 1: Project Scoping and Planning
WP1
2019-11-27 | 2020-02-03 | Research the different types of bike components
2019-12-02 | 2020-02-05 | Create a set of weighted criteria for choosing the base technology for the frame kit
| 2020-02-05 | Research Mechanical Design Synthesis
| 2020-02-06 | Develop Design Specification for kit
| 2020-02-06 | Carry out morphological design for kit
| 2020-02-06 | Sketch final concept
| 2020-02-06 | Develop criteria based on concept, specification, and last year's report
| 2020-02-06 | Decide on weights and scoring system
2019-12-07 | 2020-02-07 | Look for available technologies online
2020-01-26 | 2020-02-10 | Look for available technologies in brick and mortar shops
2020-01-29 | 2020-02-13 | Score each technology based on the weighted criteria chosen earlier
2020-01-30 | 2020-02-14 | Choose products that work well together from the top scoring options
WP2
2020-02-03 | 2020-02-14 | Create simplified CAD models of recommended components
| 2020-02-17 | Develop criteria for geometries/ assemblies
2020-02-03 | 2020-02-18 | Develop and refine concepts for one or two initial geometries
2020-02-06 | 2020-02-18 | Put together a kit with preliminary angles, lengths, and quantities of components based on concepts
2020-02-07 | 2020-02-19 | Create initial and alternative geometries from the kit and assess if they are fit for purpose
2020-02-10 | 2020-02-20 | Adjust lengths, angles, and quantities of components in the kit
2020-02-12 | 2020-02-20 | Repeat until geometries are optimised
| 2020-02-21 | Create scale models of components from cardboard, lasercut MDF, or 3D printing
2020-02-19 | 2020-02-24 | Analyse final geometries eg. Force calculations, FEA
2020-02-26 | 2020-02-26 | Decide which components should be in the starter kit and which should be add-ons
WP3
throughout, build should be documented photographically
2020-02-15 | 2020-02-22 | Source materials eg tubes
2020-02-27 | 2020-02-27 | Cut profiles to length etc.
2020-02-27 | 2020-02-28 | Fabricate any custom parts needed
2020-02-15 | 2020-02-21 | Source bicycle components eg gears
| 2020-02-01 | Prepare for presentation
2020-03-05 | 2020-03-04 | Assemble the bicycle
2020-03-03 | 2020-03-06 | Assessment 2: Preliminary Project Presentations
2019-03-12 | 2019-03-12 | Conduct testing, ie strain gauges, safety/usability assesment
WP4
2019-11-27 | 2020-02-03 | Set up GitHub repository
| 2020-02-03 | Learn MarkDown syntax
| 2019-11-27 | Track progress throughout project
| 2020-02-05 | Type up backlog of meeting minutes etc on Github
| 2020-03-12 | Write instructions on the use of the kit, based on best practice
| 2020-03-19 | Compile and finalise documantation
| 2020-03-19 | IF TIME PERMITS do extras such as feedback from target market
Report
2020-03-28 | 2020-03-30 | Compile design logs, test reports, etc.
| 2020-04-01 | Reflect on how the project could be developed in the future
| 2020-04-02 | Plan structure of report
| 2020-04-03 | List and gather all figures needed
| 2020-04-06 | Create report skeleton
| 2020-04-07 | Draft each section
| 2020-04-13 | Revise drafts
| 2020-04-20 | Work on formatting and graphics
| 2020-03-24 | Create bibliography from references (which should be collected throughout)
2020-04-29 | 2020-04-29 | Assessment 3: Final Project Report
2020-05-11 | 2020-05-11 | Assessment 5: Viva, Final Presentation and Poster
2020-05-25 | 2020-05-25 | Exhibition, External Viva